## Sheet1
Development Timeline for New Course or Scenario

Enter Date Course will be delivered:		Date Completed
2/1/2016	date format should be 1/1/2015

11/23/2015	(-10 wks) / Course Director submits Course Planning Form to simulation@uab.edu / Course Director schedules course by emailing simulation@uab.edu / Course Director schedules Pilot at least 2 weeks before course / Sim Administrator forwards Course Planning Form to appropriate OIPS Educator / OIPS Educator schedules time in next two weeks to meet with Course Director
12/7/2015	(-8 wks) / OIPS Educator Meets with Course Director / Course Director begins Scenario Template(s) / OIPS Educator assists Course Director in completing scenario template, as needed
12/21/2015	(-6 wks) / Course Director submits Scenario Template(s) to simulation@uab.edu / Sim Administrator forwards completed Scenario Template(s) to Chair of Simulation Curriculum Committee
1/4/2016	(-4 wks) / Chair of Simulation Curriculum returns decision directly to Course Director / Course Director sends final scenario template to simulation@uab.edu with changes, if necessary
1/18/2016	(-2 wks) / Course is piloted
2/1/2016	Course is delivered / Evaluations are completed
2/15/2016	(+2 wks) / Summary of evaluations are emailed to Course Director
2/29/2016	(+ 4wks) / Course Director works with OIPS Liaison to complete a Course Timeline / Course Director submits completed Course Timeline to simulation@uab.edu

	Version 01.01 September 2015